## Burn Down Chart
Project: | CST326
Sprint # | 1
| User Story ID | User Story | Task | Assigned To | Estimate (days) | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
| 1 | Web page UI | Main index page | Michael Duisenberg | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Registration page | Michael Duisenberg | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Login Page | Austin Driver | 1
|  |  | User Page | Zac Almas | 1
|  |  | Admin Page | Zac Almas | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | CSS stuffs | Michael Duisenberg, Austin Driver, Zac Almas | 1
| 2 | Database implementation | CRUD design with Admin privileges | Michael Duisenberg, Austin Driver, Zac Almas | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | Important Feature | Sending Random Email generator confirmation | Michael Duisenberg | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Upload picture at the end of the visit. | Austin Driver | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Auto-reminder email | Zac Almas | 14
|  |  | Reservation and cancel reservation feature | Michael Duisenberg, Austin Driver, Zac Almas | 7
| 4 | Admin Privilges | Print report | Michael Duisenberg | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Create another admin | Austin Driver | 14 | 0 | 0 |  | 0 | 0 | 0 | 0
|  |  | All the CRUD privileges | Zac Almas | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 100 | 90 | 80 | 70 | 60 | 50 | 40 | 30 | 20 | 10 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100

## Project Backlog
User Stories
ID | Feature | As a(n) <actor> | I would like to <description> | So that I can | Estimate (days) | Assigned To | Sprint #
1 | Web UI | app user and Admin | have a clear UI with Main page, Login, Registration, user page and Admin page | Navigate through my application | 19 | Michael Duisenberg, Austin Driver, Zac Almas | 1
2 | Database Implementation | app user and admin | have my information saved to the database with full CRUD design | keep track with the customers that come into my house | 14 | Michael Duisenberg, Austin Driver, Zac Almas | 1
3 | Important featurs | app user and admin | Be able to receive confirmation emails, reminder email, upload picture at the end of my visit, and reserve and cancel my appointment | Have better control security over my house visit | 35 | Michael Duisenberg, Austin Driver, Zac Almas | 1
4 | Admin Privileges | app admin | print reports, create another admin user, and have full CRUD access to my website | overlook the operation of my website. | 42 | Michael Duisenberg, Austin Driver, Zac Almas | 1

## How To Use
Step 1 | Hold a Sprint Planning meeting on Day 1 of of your Sprint where you will complete or update your User Stories as well as (re)prioritize your User Stories in your Product Back Log (ideally this should be done for the next 3-4 Sprints)
Step 2 | Copy the User Stories you plan to complete for this Sprint into your Sprint Back Log
Step 3 | Copy the User Stories you plan to complete from your Sprint Back Log into Column C
Step 4 | Break the User Story into a series of step by step development tasks in Column D
Step 5 | Estimate the User Story (in 1, 2, 4 or 8 Effort Man Hours) in Column F and if the task is larger than 8 hours break the User Story into multiple User Stories
Step 6 | Assign the User Story to a single Team Member in Column E
Step 7 | Repeat steps 4-6 for each User Story that has been planned for this Sprint
Step 8 | At the end of each day each Team Member should update the effort hours that were worked on their User Story to burn their work down
Step 9 | After each Daily Standup each Team Member should review the Burn Down Chart to ensure your Sprint will be delivered on time